## Start
TxDOT HIGHWAY CONSTRUCTION BID PROGRAM
Unit-price proposal worksheet · Dallas District example · 2024 Standard Specifications
This workbook prices a TxDOT highway proposal the way a contractor builds a bid: direct unit cost, job overhead, bond, insurance, profit, Item 500 mobilization, and the electronic bid guaranty. It does not submit a bid. Official proposals go through iCX (Integrated Contractor Exchange) after prequalification. Yellow cells with blue type are inputs. Green type is a cross-sheet formula. Replace the sample project before use.
HOW TO USE THIS WORKBOOK
Step | Sheet | What you do
1 | Project | Enter contractor, CSJ, highway, letting, engineer's estimate, working days, bidding capacity, and DBE goal.
2 | Markups | Set field overhead, duration, bond rate, insurance, home-office, and profit. The sheet solves a loaded bid that recovers those costs.
3 | Unit Cost | Build direct cost for production items from crew-day production, labor, equipment, material, waste, and subcontract.
4 | Bid Proposal | Confirm quantities from the proposal bid insert. Override any unit price. Blank override uses the loaded price.
5 | Mobilization | Price Item 500. Payment is staged under the 2024 spec and is capped relative to the contract on early estimates.
6 | Bond & Checks | Confirm the 2% bid guaranty, capacity, major items, zero prices, and mobilization share before iCX lock.
RULES THIS MODEL FOLLOWS
Bid form | Unit price on every bid item. Total bid is the sum of quantity × unit price. A blank unit price is a non-responsive risk.
Bid guaranty | Required when the engineer's estimate exceeds $25,000. Amount is 2% of the estimate, rounded to the nearest $1,000, not to exceed $100,000. Electronic bids require an electronic bid bond (Surety2000 or Surepath).
iCX | Prequalified contractors bid in iCX. Paper bonds and checks are not bid guaranties on electronic bids. Bids must be in the vault by the letting time. Addenda must be acknowledged.
Capacity | Bidding capacity is set from the confidential questionnaire: net working capital × TxDOT factor. A bid over remaining capacity can be rejected.
Major item | An item whose extended amount is at least 5% of the original contract or $100,000, whichever is less. Major items stay major.
Item 500 | 2024 Mobilization is paid in stages (bond/insurance invoice, plant setup cap, then 1% / 5% / 10% earned). Early payments are the lesser of a percent of the lump sum and a percent of the contract. A very high mobilization bid draws review and slows cash.
Unbalance | TxDOT reviews materially unbalanced bids (front-loaded or token prices on items likely to overrun). This sheet flags $0 prices, penny prices, and unit prices outside the benchmark band.
DBE / federal | Federal-aid jobs carry a DBE goal. Commitment forms are part of the proposal, not a line on the bid schedule.
DISCLAIMER · Not an official TxDOT form and not a substitute for the proposal, plans, general notes, or special provisions. Benchmark prices are planning figures drawn from published 2025–26 letting summaries (median low-bidder prices on common items) and typical Texas unit-price ranges. They are not TxDOT's official average low bid prices. Pull current district tabs from the TxDOT Bid Tabulations dashboard and data.texas.gov before you lock a number. Spec payment language is summarized from the 2024 Item 500; confirm the special provision actually in the proposal (SP 500-001 applies on large jobs).
Import | Paste the Whitley & Siddons EasyLinkPro export on WS Import. Proposal, estimate, and bond read that sheet.

## WS Import
WHITLEY & SIDDONS IMPORT
EasyLinkPro export · paste the job header, then paste bid items under row 15
In EasyLinkPro, open the job and export the bid-item list to Excel. Paste the control (CSJ), highway, county, district, letting date, and engineer's estimate into the yellow header. Paste item rows starting at row 16, under these columns. Accepted W&S names: Bid Item, Item, Item Number, Bid Code, Item Code; Description or Bid Item Description; Unit or UOM; Quantity, Qty, or Bid Qty. Codes can be 500-7001, 500 7001, or 5007001. Clear old rows before a new job. Direct cost and unit-price overrides stay on BidProposal.
JOB HEADER |  |  | FROM THE W&S JOB LINE
CSJ / control | 0047-14-128 |  | Engineer's estimate | 2850000 | W&S column: Estimate
Highway | US 75 |  | Description | Mill, overlay, safety, and drainage
Limits | SH 121 to FM 455 |  | Working days | 140 | From the proposal if W&S index does not carry it
County | Collin |  | Items pasted | 33
District | Dallas |  | Status | Proposal is reading this sheet
Letting date | 2026-11-04
Bid Item / Item Number / Bid Code | Description / Bid Item Description | Unit / UOM | Quantity / Qty / Bid Qty | Optional | Engineer unit, reference only | Normalized
Bid code | Description | Unit | Quantity | Category | Eng. unit | Code used
500-7001 | Mobilization | LS | 1 | Mobilization |  | 500-7001
502-7001 | Barricades, signs and traffic handling | MO | 7 | Traffic control |  | 502-7001
503-7001 | Portable changeable message sign | DAY | 140 | Traffic control |  | 503-7001
505-7001 | TMA (stationary) | DAY | 140 | Traffic control |  | 505-7001
505-7003 | TMA (mobile operation) | DAY | 30 | Traffic control |  | 505-7003
506-7039 | Temp sedmt cont fence (install) | LF | 4200 | SW3P |  | 506-7039
506-7041 | Temp sedmt cont fence (remove) | LF | 4200 | SW3P |  | 506-7041
100-7002 | Preparing right of way | STA | 18 | Earthwork |  | 100-7002
104-7006 | Removing conc (pav) | SY | 2800 | Earthwork |  | 104-7006
110-7001 | Excavation (roadway) | CY | 8600 | Earthwork |  | 110-7001
132-7005 | Embankment (final)(ord comp)(ty C) | CY | 4100 | Earthwork |  | 132-7005
164-7002 | Broadcast seed (perm)(rural)(clay) | SY | 18000 | Roadside |  | 164-7002
168-7001 | Vegetative watering | TGL | 380 | Roadside |  | 168-7001
247-7194 | Flex base (compl in place)(ty A gr 4) | CY | 3400 | Base |  | 247-7194
310-7004 | Prime coat | GAL | 14000 | Paving |  | 310-7004
354-7051 | Plane asph conc pav (2 in) | SY | 64000 | Paving |  | 354-7051
3076-7008 | D-GR HMA ty B PG64-22 | TON | 2600 | Paving |  | 3076-7008
3076-7022 | D-GR HMA ty D SAC-B PG70-22 | TON | 7400 | Paving |  | 3076-7022
432-7001 | Riprap (conc)(4 in) | CY | 160 | Drainage |  | 432-7001
464-7005 | RC pipe (cl III)(24 in) | LF | 720 | Drainage |  | 464-7005
465-7127 | Inlet (compl)(ty C) | EA | 6 | Drainage |  | 465-7127
467-7308 | SET (ty II)(24 in)(RCP)(6:1)(P) | EA | 4 | Drainage |  | 467-7308
529-7009 | Curb and gutter (ty II) | LF | 3200 | Roadside |  | 529-7009
531-7001 | Conc sidewalks (4 in) | SY | 1100 | Roadside |  | 531-7001
540-7001 | MTL W-beam GD fen (tim post) | LF | 900 | Safety |  | 540-7001
544-7001 | Guardrail end treatment (install) | EA | 6 | Safety |  | 544-7001
644-7073 | Remove sm rd sn sup & am | EA | 22 | Signing |  | 644-7073
644-7001 | Install sm rd sn sup & am | EA | 16 | Signing |  | 644-7001
666-7172 | Refl pav mrk ty I (W) 4 in (sld)(100mil) | LF | 48000 | Markings |  | 666-7172
666-7175 | Refl pav mrk ty I (Y) 4 in (sld)(100mil) | LF | 26000 | Markings |  | 666-7175
672-7004 | Refl pav mrkr ty II-A-A | EA | 820 | Markings |  | 672-7004
677-7001 | Elim ext pav mrk & mrks (4 in) | LF | 74000 | Markings |  | 677-7001
512-7001 | Port CTB (furn & inst)(safety shaped) | LF | 400 | Traffic control |  | 512-7001

## Summary
BID SUMMARY
US 75 · SH 121 to FM 455 · Dallas District · North Texas Paving, LLC
BID BY CATEGORY
Category | Bid amount | Share | Direct cost
Mobilization | 134053.4906 | 5.213% | 0
Traffic control | 117701.3646 | 4.577% | 83100
SW3P | 18076.4368 | 0.703% | 12762.4
Earthwork | 239185.7288 | 9.302% | 168870.8889
Base | 176511.4439 | 6.864% | 124621.3333
Paving | 1336351.3428 | 51.97% | 943496.254
Drainage | 178646.593 | 6.947% | 126128.8
Roadside | 215648.9406 | 8.386% | 152253.3492
Safety | 61986.5526 | 2.411% | 43764
Signing | 17690.6142 | 0.688% | 12490
Markings | 75537.176 | 2.938% | 53331.0667
Total | 2571389.684 | 100% | 1720818.0921
OUTCOME
Total bid | 2571389.684
Engineer's estimate | 2850000
Variance to estimate | -278610.316
Variance percent | -9.776%
Bid guaranty | 57000
Capacity headroom | 9028610.316

## Project
PROJECT SETUP
Sample job is a Collin County mill-and-overlay with safety and drainage. Replace every yellow cell with the proposal in hand.
CONTRACTOR |  | PROJECT
Legal name | North Texas Paving, LLC | CSJ | 0047-14-128 | From WS Import. Paste the Whitley & Siddons job line there.
TxDOT vendor ID | VT00000000 | Highway | US 75
Estimator | Estimator | Limits | SH 121 to FM 455
Date prepared | 2026-10-02 | County | Collin
|  | District | Dallas
|  | Letting date | 2026-11-04
|  | Spec book | 2024
MONEY AND TIME |  | BID POLICY INPUTS
Engineer's estimate | 2850000 | Funding | Federal-aid
Working days | 140 | DBE goal | 8%
Months on site | 7 | Mobilization target share | 5.5% | Share of work items, before Item 500. Cash and review flag, not a spec cap on the bid.
Bidding capacity | 18000000 | Contingency on direct | 2% | Unallocated field risk. Sits in the load, not as a bid item.
Capacity already committed | 6400000 | Proposal addenda received | 0 | Count of addenda acknowledged in iCX. Must match the letting.
Remaining capacity | 11600000
LIVE SNAPSHOT · updates from the Bid Proposal
Work-item direct cost | 0.035 | Capacity headroom is remaining prequalification capacity minus this bid. A negative number means this proposal, stacked on work already committed, exceeds the bidding capacity on the confidential questionnaire. TxDOT can reject a bid that exceeds available capacity. Capacity is net working capital times the factor in the approval letter — enter the letter amount, not a guess from revenue.
Loaded work-item bid | 2091234.4539
Item 500 mobilization bid | 134053.4906
Total bid | 2571389.684
Bid vs engineer's estimate | -9.776%
Bid guaranty required | 57000
Capacity headroom after this bid | 9028610.316

## Markups
INDIRECTS, BOND, INSURANCE, PROFIT
Rates load the work items. Item 500 is priced on the Mobilization sheet so bond cash is not double-counted.
JOB OVERHEAD AND RATES
Field overhead per month | 48000 | Superintendent, pickup, field office, small tools, sanitation.
Months on site | 7 | From Project.
Field overhead total | 336000 | Fixed cost spread across work items.
Bond rate on contract amount | 0.9% | Payment and performance bond. Often 0.6% to 1.5%.
Insurance rate on contract amount | 1.8% | GL, builder's risk, umbrella. Workers' comp belongs in the labor rate.
Home-office rate on contract amount | 3.5% | G&A share assigned to this job.
Profit on contract amount | 8% | Target margin on the loaded work-item total, before Item 500.
Contingency on direct | 2% | From Project. Applied to direct cost, then loaded.
LOAD SOLVE · work items only, Item 500 excluded
Direct cost of work items | 1720818.0921 | Sum of quantity × direct unit cost, excluding Item 500.
Contingency dollars | 34416.3618 | Contingency rate times direct.
Direct + contingency + field overhead | 2091234.4539 | Numerator of the load.
Rate load (bond + insurance + G&A + profit) | 14.2% | These rates apply to the loaded work-item bid.
Loaded work-item bid | 2437336.1934 | C = (direct + contingency + field OH) / (1 − bond − insurance − G&A − profit).
Markup factor on direct | 1.4164 | Suggested unit price = direct unit × this factor, unless overridden.
Dollars of load | 716518.1013 | Overhead, contingency, bond, insurance, G&A, and profit.
Why the division: bond, insurance, home office, and profit are percents of the bid, not of direct cost. Adding them on top of direct understates the bid. The solve grosses them up so the rates land on the contract amount. If you override unit prices on the proposal, the Bid Proposal sheet shows whether the overrides still recover this load.
WHERE THE LOAD GOES
Component | Amount | Share of loaded work bid
Direct work | 1720818.0921 | 70.6%
Contingency | 34416.3618 | 1.412%
Field overhead | 336000 | 13.79%
Bond | 21936.0257 | 0.9%
Insurance | 43872.0515 | 1.8%
Home office | 85306.7668 | 3.5%
Profit | 194986.8955 | 8%
Loaded work-item bid | 2437336.1934 | 100%

## Unit Cost
DIRECT UNIT COST BUILDUP
Crew-day method. Direct unit = labor/day÷production + equipment/day÷production + material×(1+waste) + subcontract. Items left off this sheet use the manual direct cost on Bid Proposal.
Bid code | Description | Unit | Production / crew-day | Labor $ / day | Equipment $ / day | Material $ / unit | Waste | Sub $ / unit | Labor $ / unit | Equip $ / unit | Material loaded | Direct $ / unit
110-7001 | Excavation (roadway) | CY | 900 | 2400 | 3100 | 0 | 5% | 0 | 2.6667 | 3.4444 | 0 | 6.1111
132-7005 | Embankment (final)(ord comp)(ty C) | CY | 750 | 2200 | 2800 | 6.5 | 8% | 0 | 2.9333 | 3.7333 | 7.02 | 13.6867
164-7002 | Broadcast seed (perm)(rural)(clay) | SY | 8000 | 1400 | 900 | 0.18 | 5% | 0 | 0.175 | 0.1125 | 0.189 | 0.4765
247-7194 | Flex base (compl in place)(ty A gr 4) | CY | 450 | 2600 | 3400 | 22 | 6% | 0 | 5.7778 | 7.5556 | 23.32 | 36.6533
310-7004 | Prime coat | GAL | 6000 | 1800 | 1600 | 2.4 | 3% | 0 | 0.3 | 0.26667 | 2.472 | 3.0387
354-7051 | Plane asph conc pav (2 in) | SY | 9000 | 2200 | 4500 | 0 | 0% | 0 | 0.24444 | 0.5 | 0 | 0.74444
3076-7022 | D-GR HMA ty D SAC-B PG70-22 | TON | 1400 | 3200 | 6800 | 78 | 4% | 0 | 2.2857 | 4.8571 | 81.12 | 88.2629
3076-7008 | D-GR HMA ty B PG64-22 | TON | 1500 | 3000 | 6400 | 68 | 4% | 0 | 2 | 4.2667 | 70.72 | 76.9867
464-7005 | RC pipe (cl III)(24 in) | LF | 160 | 2400 | 1800 | 68 | 3% | 0 | 15 | 11.25 | 70.04 | 96.29
529-7009 | Curb and gutter (ty II) | LF | 350 | 2100 | 900 | 14.5 | 5% | 0 | 6 | 2.5714 | 15.225 | 23.7964
531-7001 | Conc sidewalks (4 in) | SY | 180 | 1800 | 700 | 38 | 5% | 0 | 10 | 3.8889 | 39.9 | 53.7889
540-7001 | MTL W-beam GD fen (tim post) | LF | 250 | 1600 | 800 | 18 | 2% | 0 | 6.4 | 3.2 | 18.36 | 27.96
666-7172 | Refl pav mrk ty I (W) 4 in (sld) | LF | 12000 | 1400 | 1100 | 0.18 | 2% | 0 | 0.11667 | 0.091667 | 0.1836 | 0.39193
666-7175 | Refl pav mrk ty I (Y) 4 in (sld) | LF | 12000 | 1400 | 1100 | 0.18 | 2% | 0 | 0.11667 | 0.091667 | 0.1836 | 0.39193
506-7039 | Temp sedmt cont fence (install) | LF | 1500 | 1200 | 400 | 1.1 | 2% | 0 | 0.8 | 0.26667 | 1.122 | 2.1887
502-7001 | Barricades, signs and traffic handling | MO | 1 | 2800 | 900 | 600 | 0% | 0 | 2800 | 900 | 600 | 4300
Labor $/day is the loaded crew (wages, payroll tax, workers' comp), not bare wage. Equipment $/day is internal rate or rented blue-book, including fuel and the operator only if the operator is not already in the labor crew. Material is delivered price. Waste covers yield loss, not sales tax if tax is already in the material price. These starter rates are Dallas-area planning figures for a 2026 letting — replace them with your quotes. HMAC material near $68–$78/ton is binder plus aggregate before haul and placement; if your quote is a furnished-and-placed subcontract, put that price in Sub and zero out labor, equipment, and material.

## BidProposal
BID PROPOSAL · UNIT PRICE SCHEDULE
CSJ 0047-14-128 US 75 SH 121 to FM 455 Collin County Dallas District Letting 2026-11-04 North Texas Paving, LLC
Yellow cells are inputs. Bid unit price uses the override if one is entered; otherwise direct unit × markup factor. Benchmarks are planning bands, not the engineer's prices. A flag is a review item, not a rejection.
Seq | Bid code | Description | Category | Unit | Quantity | Manual direct | Buildup direct | Direct amount | Factor | Suggested unit | Override unit | Bid unit price | Bid amount | % of bid | Bench low | Bench typical | Bench high | Flag
1 | 500-7001 | Mobilization | Mobilization | LS | 1 | 0 | 0 | 0 | 1 | 134053.4906 |  | 134053.4906 | 134053.4906 | 5.213% | 80000 | 250000 | 450000 | OK
2 | 502-7001 | Barricades, signs and traffic handling | Traffic control | MO | 7 | 0 | 4300 | 30100 | 1.4164 | 6090.4437 |  | 6090.4437 | 42633.1056 | 1.658% | 1800 | 3900 | 8000 | OK
3 | 503-7001 | Portable changeable message sign | Traffic control | DAY | 140 | 55 | 0 | 7700 | 1.4164 | 77.901 |  | 77.901 | 10906.1433 | 0.4241% | 40 | 90 | 145 | OK
4 | 505-7001 | TMA (stationary) | Traffic control | DAY | 140 | 185 | 0 | 25900 | 1.4164 | 262.0307 |  | 262.0307 | 36684.3002 | 1.427% | 50 | 150 | 300 | OK
5 | 505-7003 | TMA (mobile operation) | Traffic control | DAY | 30 | 220 | 0 | 6600 | 1.4164 | 311.6041 |  | 311.6041 | 9348.1228 | 0.3635% | 40 | 110 | 450 | OK
6 | 506-7039 | Temp sedmt cont fence (install) | SW3P | LF | 4200 | 0 | 2.1887 | 9192.4 | 1.4164 | 3.1 |  | 3.1 | 13019.9522 | 0.5063% | 3.25 | 4 | 5.5 | OK
7 | 506-7041 | Temp sedmt cont fence (remove) | SW3P | LF | 4200 | 0.85 | 0 | 3570 | 1.4164 | 1.2039 |  | 1.2039 | 5056.4846 | 0.1966% | 0.75 | 1 | 1.5 | OK
8 | 100-7002 | Preparing right of way | Earthwork | STA | 18 | 1400 | 0 | 25200 | 1.4164 | 1982.9351 |  | 1982.9351 | 35692.8326 | 1.388% | 800 | 1500 | 2800 | OK
9 | 104-7006 | Removing conc (pav) | Earthwork | SY | 2800 | 12.5 | 0 | 35000 | 1.4164 | 17.7048 |  | 17.7048 | 49573.3786 | 1.928% | 8 | 14 | 22 | OK
10 | 110-7001 | Excavation (roadway) | Earthwork | CY | 8600 | 0 | 6.1111 | 52555.5556 | 1.4164 | 8.6557 |  | 8.6557 | 74438.7558 | 2.895% | 8 | 12 | 18 | OK
11 | 132-7005 | Embankment (final)(ord comp)(ty C) | Earthwork | CY | 4100 | 0 | 13.6867 | 56115.3333 | 1.4164 | 19.3856 |  | 19.3856 | 79480.7618 | 3.091% | 8 | 14 | 22 | OK
12 | 164-7002 | Broadcast seed (perm)(rural)(clay) | Roadside | SY | 18000 | 0 | 0.4765 | 8577 | 1.4164 | 0.67491 |  | 0.67491 | 12148.3105 | 0.4724% | 0.35 | 0.65 | 1.1 | OK
13 | 168-7001 | Vegetative watering | Roadside | TGL | 380 | 22 | 0 | 8360 | 1.4164 | 31.1604 |  | 31.1604 | 11840.9556 | 0.4605% | 12 | 26 | 50 | OK
14 | 247-7194 | Flex base (compl in place)(ty A gr 4) | Base | CY | 3400 | 0 | 36.6533 | 124621.3333 | 1.4164 | 51.9151 |  | 51.9151 | 176511.4439 | 6.864% | 32 | 45 | 62 | OK
15 | 310-7004 | Prime coat | Paving | GAL | 14000 | 0 | 3.0387 | 42541.3333 | 1.4164 | 4.3039 |  | 4.3039 | 60254.7892 | 2.343% | 3 | 4.5 | 6.5 | OK
16 | 354-7051 | Plane asph conc pav (2 in) | Paving | SY | 64000 | 0 | 0.74444 | 47644.4444 | 1.4164 | 1.0544 |  | 1.0544 | 67482.7452 | 2.624% | 1.4 | 2.4 | 3.8 | OK
17 | 3076-7008 | D-GR HMA ty B PG64-22 | Paving | TON | 2600 | 0 | 76.9867 | 200165.3333 | 1.4164 | 109.0425 |  | 109.0425 | 283510.6243 | 11.03% | 85 | 105 | 130 | OK
18 | 3076-7022 | D-GR HMA ty D SAC-B PG70-22 | Paving | TON | 7400 | 0 | 88.2629 | 653145.1429 | 1.4164 | 125.0139 |  | 125.0139 | 925103.1841 | 35.98% | 95 | 118 | 145 | OK
19 | 432-7001 | Riprap (conc)(4 in) | Drainage | CY | 160 | 145 | 0 | 23200 | 1.4164 | 205.3754 |  | 205.3754 | 32860.0681 | 1.278% | 110 | 165 | 220 | OK
20 | 464-7005 | RC pipe (cl III)(24 in) | Drainage | LF | 720 | 0 | 96.29 | 69328.8 | 1.4164 | 136.3834 |  | 136.3834 | 98196.0814 | 3.819% | 95 | 125 | 155 | OK
21 | 465-7127 | Inlet (compl)(ty C) | Drainage | EA | 6 | 4200 | 0 | 25200 | 1.4164 | 5948.8054 |  | 5948.8054 | 35692.8326 | 1.388% | 3200 | 4800 | 6500 | OK
22 | 467-7308 | SET (ty II)(24 in)(RCP)(6:1)(P) | Drainage | EA | 4 | 2100 | 0 | 8400 | 1.4164 | 2974.4027 |  | 2974.4027 | 11897.6109 | 0.4627% | 1400 | 2400 | 3600 | OK
23 | 529-7009 | Curb and gutter (ty II) | Roadside | LF | 3200 | 0 | 23.7964 | 76148.5714 | 1.4164 | 33.7048 |  | 33.7048 | 107855.4846 | 4.194% | 28 | 36 | 48 | OK
24 | 531-7001 | Conc sidewalks (4 in) | Roadside | SY | 1100 | 0 | 53.7889 | 59167.7778 | 1.4164 | 76.1856 |  | 76.1856 | 83804.19 | 3.259% | 55 | 72 | 95 | OK
25 | 540-7001 | MTL W-beam GD fen (tim post) | Safety | LF | 900 | 0 | 27.96 | 25164 | 1.4164 | 39.602 |  | 39.602 | 35641.8428 | 1.386% | 28 | 36 | 48 | OK
26 | 544-7001 | Guardrail end treatment (install) | Safety | EA | 6 | 3100 | 0 | 18600 | 1.4164 | 4390.785 |  | 4390.785 | 26344.7098 | 1.025% | 2800 | 3375 | 4200 | OK
27 | 644-7073 | Remove sm rd sn sup & am | Signing | EA | 22 | 95 | 0 | 2090 | 1.4164 | 134.5563 |  | 134.5563 | 2960.2389 | 0.1151% | 80 | 110 | 160 | OK
28 | 644-7001 | Install sm rd sn sup & am | Signing | EA | 16 | 650 | 0 | 10400 | 1.4164 | 920.6485 |  | 920.6485 | 14730.3754 | 0.5729% | 450 | 780 | 1200 | OK
29 | 666-7172 | Refl pav mrk ty I (W) 4 in (sld)(100mil) | Markings | LF | 48000 | 0 | 0.39193 | 18812.8 | 1.4164 | 0.55513 |  | 0.55513 | 26646.1159 | 1.036% | 0.45 | 0.75 | 1.15 | OK
30 | 666-7175 | Refl pav mrk ty I (Y) 4 in (sld)(100mil) | Markings | LF | 26000 | 0 | 0.39193 | 10190.2667 | 1.4164 | 0.55513 |  | 0.55513 | 14433.3128 | 0.5613% | 0.45 | 0.75 | 1.15 | OK
31 | 672-7004 | Refl pav mrkr ty II-A-A | Markings | EA | 820 | 4.4 | 0 | 3608 | 1.4164 | 6.2321 |  | 6.2321 | 5110.3071 | 0.1987% | 4 | 5.2 | 7.5 | OK
32 | 677-7001 | Elim ext pav mrk & mrks (4 in) | Markings | LF | 74000 | 0.28 | 0 | 20720 | 1.4164 | 0.39659 |  | 0.39659 | 29347.4401 | 1.141% | 0.18 | 0.35 | 0.55 | OK
33 | 512-7001 | Port CTB (furn & inst)(safety shaped) | Traffic control | LF | 400 | 32 | 0 | 12800 | 1.4164 | 45.3242 |  | 45.3242 | 18129.6927 | 0.7051% | 22 | 34 | 48 | OK
TOTAL BID | [12 empty] | 2571389.684 | 100%
Direct cost (all items) | [12 empty] | 1720818.0921
Load recovered (bid − direct, work items) | [12 empty] | 716518.1013
Load target from Markups | [12 empty] | 716518.1013
Unrecovered load | [12 empty] | 0
Bid vs engineer's estimate | [12 empty] | -9.776%

## Mobilization
ITEM 500 · MOBILIZATION
2024 Standard Item 500. Confirm the special provision in the proposal — SP 500-001 adds steps on jobs of $150 million and up.
PRICING
Work-item bid (excludes Item 500) | 2437336.1934 | From the proposal, so an override on a work item flows here.
Target share of work items | 5.5% | From Project. Planning target, not a specification maximum.
Target mobilization | 134053.4906
Known early costs to park in Item 500 | 85000 | Bond premium, insurance deposit, yard and plant move you want paid from mobilization.
Override lump sum (blank = use target) |  | Type a number to force the Item 500 bid. Leave blank to use the target.
Suggested Item 500 unit price | 134053.4906 | This is what Bid Proposal uses when the Item 500 override is blank.
Item 500 bid on the proposal | 134053.4906
Mobilization share of total bid | 5.213%
Review flag | Within ordinary range
2024 PAYMENT SCHEDULE · lesser of the lump-sum step and the contract cap
Payment event | Lump-sum step | Contract cap | Amount this schedule pays
Bond, insurance invoice (as incurred) | 85000 | 134053.4906 | 85000
Plant / facility setup | 13405.3491 | 13405.3491 | 13405.3491
When 1% of construction items earned | 67026.7453 | 128569.4842 | 0
When 5% of construction items earned | 100540.118 | 257138.9684 | 2134.7689
When 10% of construction items earned | 120648.1416 | 257138.9684 | 20108.0236
Remainder with final mobilization closeout | 134053.4906 | 134053.4906 | 13405.3491
Check — schedule equals Item 500 bid |  |  | 134053.4906
Material on hand does not count as work earned for these steps. The plant-setup payment is the lesser of 10% of the mobilization lump sum and 1% of the contract. Each later step pays the lesser of the lump-sum percent and the contract percent, minus what has already been paid. A mobilization bid above about 10% of the contract usually fails the early-pay caps, so the cash sits until the end. Callout and emergency contracts are paid differently — do not use this schedule for those.

## Bond & Checks
BID GUARANTY, CAPACITY, AND CHECKS
43 TAC §9.14 and Item 2. Electronic bids need an electronic bid bond. Paper checks are not a guaranty on an iCX bid.
BID GUARANTY
Engineer's estimate | 2850000 | From Project.
Guaranty required? | Yes | Required when the estimate on advertisement day is over $25,000.
2% of estimate | 57000 | Starting point before rounding.
Rounded to nearest $1,000 | 57000 | Statute rounds to the nearest $1,000.
Statutory cap | 100000 | Not to exceed $100,000.
Bid guaranty amount | 57000 | Enter this authorization in iCX. Surety2000 or Surepath.
CAPACITY
Approved bidding capacity | 18000000
Already committed | 6400000
This bid | 2571389.684
Headroom if awarded | 9028610.316
Capacity check | Within capacity
RESPONSIVENESS CHECKS
Items with a zero unit price | 0
Token / penny prices | 0
Under benchmark band | 0
Over benchmark band | 0
Mobilization over 10% | 0
Major items (5% or $100,000, lesser test) | 5
Unrecovered load | 0
DBE goal (federal-aid) | 8%
A major item is any bid item whose extension is at least 5% of the original contract or $100,000, whichever is less. Zero prices and token prices on items that can overrun are the usual unbalanced-bid problems. Band flags compare your unit price to the planning benchmark on that row — a flag means look at the bid tabs, not that the price is wrong. DBE commitment is a form in the proposal, not a deduction from the bid.

## Checklist
LETTING CHECKLIST
Status is an input. This list follows Item 2, the confidential questionnaire, and iCX practice. It is not the proposal.
# | Gate | Requirement | Status | Owner
1 | Qualify | Confidential questionnaire and audited financials current. Bidding capacity letter in hand. | Not started | Estimator
2 | iCX | Administrative account live. Bidders have their own emails. Passwords not shared. | Not started | Admin
3 | Bond | Electronic bid bond set up with Surety2000 or Surepath. Allow a week the first time. | Not started | Surety
4 | Proposal | Bid insert quantities match this sheet. No item skipped. | Not started | Estimator
5 | Addenda | Every addendum acknowledged in iCX. Count matches Project!F19. | Not started | Estimator
6 | Plans | General notes, traffic control plan, and SW3P read. Quantity conflicts written down. | Not started | Estimator
7 | DBE | If federal-aid, DBE commitment meets the goal or a good-faith memo is ready. | Not started | Estimator
8 | Prices | Zero-price and token-price flags cleared or explained. | Not started | Estimator
9 | Mobilization | Item 500 covers bond and move-in, and the share is a number you can defend. | Not started | Estimator
10 | Capacity | This bid plus committed work fits remaining capacity. | Not started | CFO
11 | Quotes | HMAC, pipe, guardrail, striping, and traffic control quotes dated inside 30 days. | Not started | Estimator
12 | Subs | Sub prices include their bond if they bond, and sales tax treatment is consistent. | Not started | Estimator
13 | Time | Working-day schedule fits the barricade months and the TMA days. | Not started | PM
14 | Vault | Bid submitted before the letting clock. Internet failure is the bidder's risk. | Not started | Admin
15 | Withdrawal | Withdrawal path tested. A bid in the vault at letting time stands. | Not started | Admin
Contacts used by TxDOT for electronic bidding setup: Construction Division letting desk, 512-416-4577. Bond clearinghouses published by TxDOT: Surety2000, 800-660-3263; Surepath, 818-783-3460. Bid tabs: TxDOT Bid Tabulations dashboard and data.texas.gov dataset Bid Tabulations.